## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-01 | As a developer, I want a Code Submission interface (direct paste & file upload) so I can submit Python and Java code for automated review. | Must Have | None | Fullstack Dev | Completed
1 | 1 | US-02 | As a developer, I want instant syntax validation (AST / javalang) so that malformed or mixed-language code is rejected before heavy analysis. | Must Have | US-01 | Backend Dev | Completed
1 | 1 | US-03 | As a security engineer, I want a RAG Knowledge Base indexing OWASP, CWE, CERT, and NIST guidelines into ChromaDB for grounded security retrieval. | Must Have | None | AI/Data Eng | Completed
2 | 2 | US-04 | As a developer, I want a Code Quality Agent using Pylint & PMD to detect code smells, bad practices, and maintainability issues. | Must Have | US-01 | Backend Dev | Completed
2 | 2 | US-05 | As a developer, I want a Security Vulnerability Agent using Bandit & SpotBugs to scan for SQLi, Command Injection, XSS, and weak crypto. | Must Have | US-01 | Security Dev | Completed
2 | 2 | US-06 | As an architect, I want LangGraph multi-agent orchestration to fan-out analysis agents in parallel and merge/deduplicate findings. | Must Have | US-04, US-05 | AI Eng | Completed
2 | 2 | US-07 | As a QA engineer, I want automated validation suites with ground-truth test files to benchmark detection accuracy (precision/recall). | Should Have | US-06 | QA Eng | Completed
3 | 3 | US-08 | As a developer, I want an automated Remediation Agent (Groq Llama 3.3 + RAG) that generates drop-in code fixes with one-click editor updates. | Must Have | US-03, US-06 | AI Eng | Completed
3 | 3 | US-09 | As a tech lead, I want a PR Summary Agent that calculates a Code Health Score (0-100) and estimates developer remediation time. | Must Have | US-08 | Backend Dev | Completed
3 | 3 | US-10 | As a developer, I want an interactive, context-aware AI Chat Assistant to ask follow-up questions about flagged vulnerabilities. | Must Have | US-03, US-08 | Fullstack Dev | Completed
3 | 3 | US-11 | As a security auditor, I want to test ChromaDB semantic retrieval directly in the UI and export scan findings as Markdown/PDF reports. | Could Have | US-03, US-09 | Frontend Dev | Completed
4 | 4 | US-12 | As a developer, I want a complete Scan History & Audit Dashboard to inspect full historical source code, review previous findings, and reload scans. | Must Have | US-01, US-06 | Fullstack Dev | Completed

## Sprint Backlog
Sprint | US ID | Task ID | Task Description | Estimated Hours | Actual Hours | Assignee | Status
Sprint 1 | US-01 | T-01.1 | Setup FastAPI gateway, SQLite schema, and REST endpoints | 6 | 5.5 | Backend Dev | Done
Sprint 1 | US-01 | T-01.2 | Build Monaco editor React interface and file upload component | 8 | 8 | Frontend Dev | Done
Sprint 1 | US-02 | T-02.1 | Implement AST parser for Python and javalang parser for Java | 5 | 4.5 | Backend Dev | Done
Sprint 1 | US-03 | T-03.1 | Curate 17 OWASP/CWE/CERT/NIST markdown reference docs | 8 | 9 | Security Dev | Done
Sprint 1 | US-03 | T-03.2 | Implement ChromaDB ingestion with all-MiniLM-L6-v2 embeddings | 6 | 5 | AI Eng | Done
Sprint 2 | US-04 | T-04.1 | Integrate Pylint & PMD rule parsers with severity mapping | 8 | 7.5 | Backend Dev | Done
Sprint 2 | US-05 | T-05.1 | Integrate Bandit & SpotBugs/FindSecBugs security rules | 10 | 11 | Security Dev | Done
Sprint 2 | US-06 | T-06.1 | Design LangGraph StateGraph, Fan-Out nodes, and Merge Node | 12 | 12.5 | AI Eng | Done
Sprint 2 | US-06 | T-06.2 | Implement rule-based deduplication and authoritative severity sorting | 6 | 5.5 | AI Eng | Done
Sprint 2 | US-07 | T-07.1 | Create ground-truth benchmarks (sample_python_vulnerabilities.py, VulnerableUserService.java) | 6 | 6 | QA Eng | Done
Sprint 3 | US-08 | T-08.1 | Build Remediation Agent prompt pipeline with Groq Llama 3.3 & RAG | 10 | 9.5 | AI Eng | Done
Sprint 3 | US-08 | T-08.2 | Build Frontend "Apply Fix" one-click patch updater & Diff Viewer | 7 | 7 | Frontend Dev | Done
Sprint 3 | US-09 | T-09.1 | Implement weighted health score algorithm (0-100) and PR summary generator | 6 | 5 | Backend Dev | Done
Sprint 3 | US-10 | T-10.1 | Build context-aware chat backend with scan memory and RAG retrieval | 8 | 8.5 | Fullstack Dev | Done
Sprint 3 | US-10 | T-10.2 | Design floating Chatbot UI with code block formatting & suggestion chips | 7 | 6.5 | Frontend Dev | Done
Sprint 3 | US-11 | T-11.1 | Implement Markdown report exporter and KBTester interactive UI | 5 | 4.5 | Frontend Dev | Done
Sprint 4 | US-12 | T-12.1 | Build GET /api/v1/submit/scan/{scan_id} and DELETE /{scan_id} cascading endpoints | 6 | 5 | Backend Dev | Done
Sprint 4 | US-12 | T-12.2 | Implement interactive History Audit Dashboard with code inspector, metrics, and search | 9 | 8.5 | Frontend Dev | Done
Sprint 4 | US-04 | T-04.2 | Refactor Java complexity nesting counter to ignore try-with-resources blocks | 4 | 3.5 | Backend Dev | Done

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Docker pgvector DB connection latency and setup friction across developer machines. | Replaced local PostgreSQL requirement with lightweight embedded ChromaDB + SQLite persistence.
Sprint 1 | Day 8 | Windows CRLF line ending differences broke javalang token line numbering. | Added universal newline normalizer (\r\n -> \n) before AST parsing.
Sprint 2 | Day 4 | SpotBugs threw Errno 13 Permission Denied inside container environment. | Updated Dockerfile with explicit chmod +x permissions for PMD and SpotBugs CLI binaries.
Sprint 2 | Day 9 | Bandit missed eval() and exec() when defined as dynamic expressions. | Added explicit B307 (eval) and B102 (exec) security mapping rules to BANDIT_OWASP_MAP.
Sprint 3 | Day 2 | Frontend fetch calls failed with ERR_CONNECTION_REFUSED due to IPv6 localhost resolution on Windows Chrome. | Updated Vite proxy and client fetch targets from localhost:8000 to explicit 127.0.0.1:8000.
Sprint 3 | Day 11 | LLM remediation occasionally returned conversational fluff instead of raw executable code. | Enforced strict JSON schema output formatting and automated code block extraction regex.
Sprint 4 | Day 3 | Try-with-resources constructs in Java were falsely flagged as excessive nesting depth of 5 levels. | Enhanced AST visitor in java_analyzer.py to skip try-with-resources declaration headers in nesting counts.
Sprint 4 | Day 8 | History view displayed only truncated 2-line code snippets without opening findings or allowing full inspection. | Implemented interactive History Dashboard with detail API integration, multi-tab code viewer, and search filters.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-06-01 | 2026-06-14 | DevSecOps Team | Documenting ground-truth test cases before writing analyzer integrations. | Relying on heavy external database dependencies for local developer setups. | Maintaining strict modularity between API gateway, services, and storage. | Switched to embedded ChromaDB and created standalone validation scripts.
2 | Sprint 2 | 2026-06-15 | 2026-06-28 | DevSecOps Team | Running static analyzers with strict OWASP rule mappings immediately upon build. | Hardcoding localhost strings across client and backend configurations. | Parallelizing independent analysis tasks using LangGraph fan-out execution. | Created automated run_tests.py and converted all fetch URLs to 127.0.0.1.
3 | Sprint 3 | 2026-06-29 | 2026-07-12 | DevSecOps Team | Cross-Encoder re-ranking on RAG chunks to eliminate LLM hallucination risks. | Permitting unbounded LLM generation without JSON schema enforcement. | Providing interactive one-click remediation directly in the developer editor. | Implemented 19-module automated validation suite (run_validation.py).
4 | Sprint 4 | 2026-07-13 | 2026-07-26 | DevSecOps Team | Comprehensive AST rule unit testing to detect edge-case false positives early. | Truncating user code snippets in audit logs without full inspection capabilities. | Continuous UI/UX polishing for developer ergonomics and seamless audit flows. | Implemented History Audit Dashboard and refined Java AST SAST rule engine.