## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US01 | As a developer, I want a code submission API so I can send snippets for analysis. | Must Have | None | AI Agent | Completed
1 | 1 | US02 | As a user, I want a RAG-based Knowledge Base to query secure coding practices. | Must Have | US01 | AI Agent | Completed
2 | 2 | US03 | As a user, I want Python and Java code analyzed for code smells (PMD/Pylint). | Must Have | US01 | AI Agent | Completed
2 | 2 | US04 | As a user, I want Python and Java code analyzed for security flaws (SpotBugs/Bandit). | Must Have | US01 | AI Agent | Completed
2 | 2 | US05 | As a user, I want a React dashboard to view and export my scan results. | Should Have | US04 | AI Agent | Completed
2 | 2 | US03 | As a developer, I want my code editor and results layout to be responsive and not vertically squished. | Must Have | None | AI Agent | Completed
2 | 2 | US04 | As a developer, I want to automatically apply suggested code fixes directly to the editor. | Must Have | US01 | AI Agent | Completed
2 | 2 | US05 | As a user, I want the AI Assistant to provide context-aware chat about security findings. | Must Have | US01 | AI Agent | Completed
2 | 2 | US06 | As a user, I want to use the latest Gemini models for enhanced PR Summaries. | Must Have | None | AI Agent | Completed

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | Day 3 | Docker pgvector DB not accessible | Wrote standalone test scripts
2 | Day 12 | Frontend fetch calls blocked by ERR_CONNECTION_REFUSED | Swapped localhost for 127.0.0.1 in Vite
2 | Day 13 | Gemini API 404 due to deprecated gemini-1.5-flash | Updated backend to use gemini-flash-latest across all agents
2 | Day 14 | UI Layout is squishing the Risk Score and right panel | Replaced hardcoded grid with flex-wrap and 50/50 CSS Grid layout
2 | Day 15 | Apply Fix API returning 404 | Corrected frontend fetch route to point to /api/v1/submit/ prefix

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 2 | 2026-07-01 | 2026-07-20 | AI Agent | Running static tools with strict rulesets immediately | Hardcoding localhost | Thorough pre-testing of docker containers | Automated tests created
2 | 3 | 2026-07-20 | 2026-07-23 | AI Agent | Dynamically handling Gemini list responses | Hardcoding LLM model versions | Providing exact HTTP response mapping | Implemented robust JSON & String extraction for Gemini responses