## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Dev | 2026-07-20 | SpotBugs throws Errno 13 Permission Denied in Docker | Sprint 2 | AI Agent | Configuration | Added chmod +x for SpotBugs/PMD binaries in Dockerfile | 2026-07-20 | Closed | Fixed in Milestone 2
2 | Dev | 2026-07-20 | Bandit analyzer misses eval() and exec() vulnerabilities | Sprint 2 | AI Agent | Logical | Added B307 and B102 mappings to BANDIT_OWASP_MAP | 2026-07-20 | Closed | Fixed in Milestone 2
3 | QA | 2026-07-20 | PMD misses UseUtilityClass and System.exit() rules | Sprint 2 | AI Agent | Logical | Updated PMD CLI args to include category/java/design.xml and errorprone.xml | 2026-07-20 | Closed | Fixed in Milestone 2
4 | QA | 2026-07-20 | Frontend fetch calls fail with ERR_CONNECTION_REFUSED on Windows Chrome | Sprint 2 | AI Agent | Network | Changed http://localhost:8000 to http://127.0.0.1:8000 in Vite fetch requests | 2026-07-20 | Closed | Fixed in Milestone 2
3 | QA | 2026-07-23 | Gemini API throws 404 NOT FOUND for gemini-1.5-flash | Sprint 2 | AI Agent | Configuration | Replaced gemini-1.5-flash with gemini-flash-latest | 2026-07-23 | Closed | Fixed
4 | QA | 2026-07-23 | Gemini returns list instead of string causing strip() crash | Sprint 2 | AI Agent | Logical | Added safe extraction of string from dictionary/list response | 2026-07-23 | Closed | Fixed
5 | QA | 2026-07-23 | Chat Assistant crashes with contents are required | Sprint 2 | AI Agent | Logical | Added fallback string for empty prompts | 2026-07-23 | Closed | Fixed
6 | QA | 2026-07-23 | Apply Fix button fails with 404 Not Found | Sprint 2 | AI Agent | Integration | Updated App.jsx to point to /api/v1/submit prefix | 2026-07-23 | Closed | Fixed
7 | User | 2026-07-23 | UI scales infinitely and requires excessive scrolling | Sprint 2 | AI Agent | User Interface | Restricted app-grid height to 100vh and added internal scrolling | 2026-07-23 | Closed | Fixed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others