## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Group1 | 2026-06-30 | [Backend] SQLite throws "Database is locked" error on concurrent requests. | Sprint 1 | Group1 | Logical | Added thread checking configuration (check_same_thread=False) to database.py engine setup. | 2026-06-30 | Closed | Root cause: SQLAlchemy engine instantiated without check_same_thread=False for SQLite.
2 | Group1 | 2026-07-01 | [UI/UX] Frontend language dropdown conflicts with backend auto-detection. | Sprint 1 | Group1 | Logical | Removed language selector UI; forced reliance on backend heuristic detection (guess_language()). | 2026-07-01 | Closed | Root cause: redundant state management in App.jsx overriding backend guess_language().
3 | Group1 | 2026-07-02 | [Backend] Code Quality agent returns raw markdown instead of valid JSON. | Sprint 2 | Group1 | Logical | Enforced LangChain JSON Output Parser and added retry-logic on parsing failures. | 2026-07-02 | Closed | Root cause: LLM ignored strict JSON schema prompt instructions.
4 | Group1 | 2026-07-03 | [Backend] Security Agent fails to detect SQL Injection in partial code snippets. | Sprint 2 | Group1 | Logical | Implemented an LLM fallback prompt to forcefully scan uncompiled snippets when static tools fail. | 2026-07-03 | Closed | Root cause: static tools (Semgrep/SpotBugs) require fully compilable code to function.
5 | Group1 | 2026-07-04 | [Frontend] CORS Error when frontend tries to hit backend API. | Sprint 1 | Group1 | Logical | Updated main.py CORS setup to allow the local frontend origin (localhost:5173). | 2026-07-04 | Closed | Root cause: FastAPI CORS Middleware was missing localhost:5173 in allowed origins.
6 | Group1 | 2026-07-05 | [UI/UX] KB Tester shows all matches as 100% or 0%. | Sprint 3 | Group1 | Logical | Applied a mathematical sigmoid function in ScoreBadge to convert raw logits to valid percentages. | 2026-07-05 | Closed | Root cause: frontend was naively capping raw Cross-Encoder logits between 0 and 1.
7 | Group1 | 2026-07-06 | [UI/UX] Layout breaks and container expands infinitely on large result sets. | Sprint 4 | Group1 | User Interface | Applied min-height: 0 to flex panels and grid-template-rows: minmax(0, 1fr) to constrain grid tracks. | 2026-07-06 | Closed | Root cause: CSS Grid implicit row height (auto) expanded to fit massive finding lists.
8 | Group1 | 2026-07-06 | [Backend] KB Tester hangs for 40 seconds on the first search. | Sprint 3 | Group1 | Maintainability | Kept lazy-load but added UI documentation explaining the one-time model download delay to the user. | 2026-07-06 | Closed | Root cause: lazy-loading the 90MB Cross-Encoder model synchronously on the first API request (SQLite + ChromaDB stack, no external DB server involved).
9 | Group1 | 2026-07-07 | [Frontend] Chat UI does not auto-scroll to the latest message. | Sprint 4 | Group1 | User Interface | Added useRef to bottom div and called scrollIntoView() on message state change. | 2026-07-07 | Closed | Root cause: missing useEffect hook to scroll chat container to bottom on message update.
Note on A1: Group1 project data (expanded dataset). Tech stack: SQLite (persistence) + ChromaDB (vector store) — no Docker or PostgreSQL used. 'Detected Sprint' inferred by matching each defect to the sprint task it relates to (see Product/Sprint Backlog tabs in Agile file for the task mapping).

## Sheet2
Logical
User Interface
Maintainability
Standards
Others